## Tasks
Task List
Task | Task Type | Start | Due | Assignee | Help URL
Business Case | Business Case | 2018-07-25 07:00 | 2018-07-26 07:00 |  | https://github.com/cinnojam/AdvanvcedCICDPipeline/wiki
z - 1. Idea Summary | Business Case | 2018-07-25 07:00 | 2018-07-26 07:00 | Shanti
z - 2. Execution Plan | Business Case | 2018-07-25 07:00 | 2018-07-26 07:00 | Shanti
z - 3. Needed Resources (high/med/low) | Business Case | 2018-07-25 07:00 | 2018-07-26 07:00 | Shanti
z - 4. Key benefits to the organization | Business Case | 2018-07-25 07:00 | 2018-07-26 07:00 | Shanti
z - 5. Risks and concerns | Business Case | 2018-07-25 07:00 | 2018-07-26 07:00 | Shanti
z - 6. Initial success criteria/kpi’s and metrics | Business Case | 2018-07-25 07:00 | 2018-07-26 07:00 | Shanti
POC | POC | 2018-07-25 07:00 | 2018-07-26 07:00
z - 1. Build the GoCD pipeline | POC | 2018-07-25 07:00 | 2018-07-26 07:00 |  | pipelines tab of this spreadsheet
z - 1.1. Build 2 CI pipelines | POC | 2018-07-25 07:00 | 2018-07-26 07:00 | Chris/Justin
z - 1.2. Build 2 DEV pipelines | POC | 2018-07-25 07:00 | 2018-07-26 07:00 | Chris/Justin
z - 1.3. Build PROD pipeline | POC | 2018-07-25 07:00 | 2018-07-26 07:00 | Chris/Justin
z - 1.4. Notifiy slack "business approval" channel when the prod pipeline "request for approval" stage is manually triggered. - Work on providing "rich" message detail. - Use message buttons | POC | 2018-07-25 07:00 | 2018-07-26 07:00 | Chris/Justin
z - 1.5. Notify the slack "deployments" channel when: - “approve” or “reject” is selected on a “business approval” channel message - a production deployment starts on GoCD - a production deployment completes on GoCD | POC | 2018-07-25 07:00 | 2018-07-26 07:00 | Chris/Justin
z - 2. Create a new slack workspace for the POC | POC | 2018-07-25 07:00 | 2018-07-26 07:00 | N/A
z - 3. Create the Jbot Slack/GoCD integration | POC | 2018-07-25 07:00 | 2018-07-26 07:00 | Brad/Josh
Z – 3.1. Fork the "Jbot" repo | POC | 2018-07-25 07:00 | 2018-07-26 07:00 | Brad/Josh | https://github.com/rampatra/jbot Slack Documentation: https://api.slack.com/docs/message-formatting https://api.slack.com/interactive-messages https://api.slack.com/docs/message-buttons
Z – 3.2. Add/update model classes for Slack interaction (RichMessage and Payload and their children) |  |  |  | Brad/Josh | Our docs at https://github.com/cinnojam/AdvanvcedCICDPipeline/tree/master/docs/slack SlackModel.txt
Z – 3.3. Create the SlackConfig file to pull slack properties from the env variables | POC | 2018-07-25 07:00 | 2018-07-26 07:00 | Brad/Josh | SlackConfig.txt
Z – 3.4. Create the SlackRestController to support Incoming Webhooks, slash commands, and interactive messages | POC | 2018-07-25 07:00 | 2018-07-26 07:00 | Brad/Josh | Slack-WebHooks.txt
Z – 3.5. Add webhooks for notifications from GoCD to Slack (business approval request, prod deploy started, & prod deploy complete) | POC | 2018-07-25 07:00 | 2018-07-26 07:00 | Brad/Josh | Slack-WebHooks.txt
Z – 3.6. Add the slash commands: “echo” & "approve" | POC | 2018-07-25 07:00 | 2018-07-26 07:00 | Brad/Josh | Slack-SlashCommands.txt
Z – 3.7. Add Interactive Message response handling (Slack → SlackBot → GoCD) | POC | 2018-07-25 07:00 | 2018-07-26 07:00 | Brad/Josh | Slack-InteractiveMessages.txt Slack-tunnel.txt
Z – 3.8. Trigger the pipeline stage from the slackbot | POC | 2018-07-25 07:00 | 2018-07-26 07:00 | Brad/Josh | Slack-InteractiveMessages.txt Slack-tunnel.txt
z - 4. Create GoCD and Slack test data & screenshots for POC & presentation content | POC | 2018-07-25 07:00 | 2018-07-26 07:00 | All | https://stackoverflow.com/questions/10888610/ignore-invalid-self-signed-ssl-certificate-in-node-js-with-https-request
Presentation | Presentation | 2018-07-25 07:00 | 2018-07-26 07:00
z - 1. Business Case (3 mins) | Presentation | 2018-07-25 07:00 | 2018-07-26 07:00 | Shanti
z - 2. Solution to the business case (2 mins) | Presentation | 2018-07-25 07:00 | 2018-07-26 07:00 | Shanti
z - 3. Demo (5 mins) | Presentation | 2018-07-25 07:00 | 2018-07-26 07:00 | Shanti
Extra credit | Extra | 2018-07-25 07:00 | 2018-07-26 07:00 | Shanti
z - 1. Implement what we can using Spinnaker | Extra | 2018-07-25 07:00 | 2018-07-26 07:00 | Shanti | https://cloud.google.com/solutions/continuous-delivery-spinnaker-kubernetes-engine

## Pipelines
[7 empty] | Pipeline Group Authz |  |  | Stage Permission
Pipeline Group | Pipeline | Stage | Job | Task | Task – empty pipeline | Description | Admin | Operate | View
Continuous Integration * set JAVA_HOME in the pipelines’ environment variables to a JDK on the host system. This is needed for MVN to compile the code from SCM. | portfolio-ci - trigger: github change | build | compile | mvn clean install | echo %GO_PIPELINE_NAME% __%GO_PIPELINE_COUNTER%__%GO_STAGE_NAME% | create jar from github code | Admins | Developers | Auditors
|  |  | build | docker-compose build | echo %GO_PIPELINE_NAME% __%GO_PIPELINE_COUNTER%__%GO_STAGE_NAME% | create a docker image and tag as “latest” | Admins | Developers | Auditors
|  |  | push | docker-compose push | echo %GO_PIPELINE_NAME% __%GO_PIPELINE_COUNTER%__%GO_STAGE_NAME% | push the docker image to docker hub | Admins | Developers | Auditors
| security-rating-ci - trigger: github change | build | compile | mvn clean install | echo %GO_PIPELINE_NAME% __%GO_PIPELINE_COUNTER%__%GO_STAGE_NAME% | create jar from github code | Admins | Developers | Auditors
|  | build | build | docker-compose build | echo %GO_PIPELINE_NAME% __%GO_PIPELINE_COUNTER%__%GO_STAGE_NAME% | create a docker image and tag as “latest” | Admins | Developers | Auditors
|  | build | push | docker-compose push | echo %GO_PIPELINE_NAME% __%GO_PIPELINE_COUNTER%__%GO_STAGE_NAME% | push the docker image to docker hub | Admins | Developers | Auditors
Continuous Deployment to Dev | portfolio-dev - trigger: portfolio-ci pipeline | deploy | k8s-auth | gcloud auth activate-service-account pipeline@portfolio-innojam.iam.gserviceaccount.com --keyfile D:\google\portfolio.json | echo %GO_PIPELINE_NAME% __%GO_PIPELINE_COUNTER%__%GO_STAGE_NAME% | connect to the cloud provider | Admins | Developers | Auditors
|  |  | k8s-deploy | kubectl apply -f <k8s “deployment” yaml> –validate=false | echo %GO_PIPELINE_NAME% __%GO_PIPELINE_COUNTER%__%GO_STAGE_NAME% | deploy the docker image to k8s cluster | Admins | Developers | Auditors
|  |  |  | kubectl rollout status deployment/portfolio --namespace=development |  | wait for the service to finish deployment | Admins | Developers | Auditors
|  | test | test | curl <dev url> | echo %GO_PIPELINE_NAME% __%GO_PIPELINE_COUNTER%__%GO_STAGE_NAME% | make sure the service responds | Admins | Developers | Auditors
|  | tag | tag | docker tag <latest tag> <new dev tag> | echo %GO_PIPELINE_NAME% __%GO_PIPELINE_COUNTER%__%GO_STAGE_NAME% | tag the docker image as “dev” | Admins | Developers | Auditors
|  |  | push | docker push <new dev tag> | echo %GO_PIPELINE_NAME% __%GO_PIPELINE_COUNTER%__%GO_STAGE_NAME% | push the tag to docker hub | Admins | Developers | Auditors
| security-rating-dev - trigger: security-rating-ci pipeline | deploy | k8s-auth | gcloud auth activate-service-account pipeline@portfolio-innojam.iam.gserviceaccount.com --keyfile D:\google\portfolio.json | echo %GO_PIPELINE_NAME% __%GO_PIPELINE_COUNTER%__%GO_STAGE_NAME% | connect to the cloud provider | Admins | Developers | Auditors
|  |  | k8s-deploy | kubectl apply -f <k8s “deployment” yaml> | echo %GO_PIPELINE_NAME% __%GO_PIPELINE_COUNTER%__%GO_STAGE_NAME% | deploy the docker image to k8s cluster | Admins | Developers | Auditors
|  |  |  | kubectl rollout status deployment/portfolio --namespace=development |  | wait for the service to finish deployment | Admins | Developers | Auditors
|  | test | test | curl <dev url> | echo %GO_PIPELINE_NAME% __%GO_PIPELINE_COUNTER%__%GO_STAGE_NAME% | make sure the service responds | Admins | Developers | Auditors
|  | tag | tag | docker tag <latest tag> <new dev tag> | echo %GO_PIPELINE_NAME% __%GO_PIPELINE_COUNTER%__%GO_STAGE_NAME% | tag the docker image as “dev” | Admins | Developers | Auditors
|  |  | push | docker push <new dev tag> | echo %GO_PIPELINE_NAME% __%GO_PIPELINE_COUNTER%__%GO_STAGE_NAME% | push the tag to docker hub | Admins | Developers | Auditors
Continuous Delivery to Prod | PortfolioManagementApplication - trigger: portfolio-dev - trigger: security-rating-dev | initiate | initiate | echo waiting for approval | echo waiting for approval | stage to initiate the pipeline for future manual approvals | Admins | BusinessApprovers Developers | Auditors | Developers
|  | ProjectTeamRequest4Approval * manual: requires approval by Developer | Notification | curl -X GET "http://localhost:8765/slack/webhook? pipeline=%GO_PIPELINE_NAME% &instance=%GO_PIPELINE_COUNTER% &stage=%GO_STAGE_NAME%" | curl -X GET "http://localhost:8765/slack/webhook? pipeline=%GO_PIPELINE_NAME% &instance=%GO_PIPELINE_COUNTER% &stage=%GO_STAGE_NAME%" | Notify business that there is a production deployment to approve | Admins | BusinessApprovers Developers | Auditors | Developers
|  | BusinessApproval * manual: requires approval by Business role prior to triggering jobs | Notification | curl -X GET "http://localhost:8765/slack/webhook? pipeline=%GO_PIPELINE_NAME% &instance=%GO_PIPELINE_COUNTER% &stage=%GO_STAGE_NAME%" | curl -X GET "http://localhost:8765/slack/webhook? pipeline=%GO_PIPELINE_NAME% &instance=%GO_PIPELINE_COUNTER% &stage=%GO_STAGE_NAME%" | Notification that a production deployment is happening | Admins | BusinessApprovers Developers | Auditors | BusinessApprovers
[7 empty] | Admins | BusinessApprovers Developers | Auditors
[7 empty] | Admins | BusinessApprovers Developers | Auditors
|  | deploy | k8s-auth | gcloud auth activate-service-account pipeline@portfolio-innojam.iam.gserviceaccount.com --keyfile D:\google\portfolio.json | echo %GO_PIPELINE_NAME% __%GO_PIPELINE_COUNTER%__%GO_STAGE_NAME% | connect to the cloud provider | Admins | BusinessApprovers Developers | Auditors | Admins
|  |  | k8s-deploy | kubectl apply -f <k8s “portfolio production deployment” yaml> | echo %GO_PIPELINE_NAME% __%GO_PIPELINE_COUNTER%__%GO_STAGE_NAME% | deploy the portfolio docker image to k8s cluster | Admins | BusinessApprovers Developers | Auditors | Admins
|  |  |  | kubectl apply -f <k8s “rating-security production deployment” yaml> |  | deploy the security-pricing docker image to k8s cluster | Admins | BusinessApprovers Developers | Auditors | Admins
|  |  |  | kubectl rollout status deployment/portfolio –namespace=production |  | wait for the portfolio service to finish deployment | Admins | BusinessApprovers Developers | Auditors | Admins
|  |  |  | kubectl rollout status deployment/security-rating –namespace=production |  | wait for the security-rating service to finish deployment | Admins | BusinessApprovers Developers | Auditors | Admins
|  | test | test | curl <prod portfolio url> | echo %GO_PIPELINE_NAME% __%GO_PIPELINE_COUNTER%__%GO_STAGE_NAME% | make sure the service responds | Admins | BusinessApprovers Developers | Auditors | Admins
|  |  |  | curl <prod rating-security url> |  | make sure the service responds | Admins | BusinessApprovers Developers | Auditors | Admins
|  | tag | tag | docker tag <dev tag> <new prod tag> | echo %GO_PIPELINE_NAME% __%GO_PIPELINE_COUNTER%__%GO_STAGE_NAME% | tag the portfolio docker image as “prod” | Admins | BusinessApprovers Developers | Auditors | Admins
|  |  | tag | docker tag <dev tag> <new prod tag> |  | tag the security-rating docker image as “prod” | Admins | BusinessApprovers Developers | Auditors | Admins
|  | push | push | docker push <new prod tag> | curl -X GET "http://localhost:8765/slack/webhook? pipeline=%GO_PIPELINE_NAME% &instance=%GO_PIPELINE_COUNTER% &stage=%GO_STAGE_NAME%" | push the portfolio tag to docker hub | Admins | BusinessApprovers Developers | Auditors | Admins
|  |  |  | docker push <new prod tag> |  | push the security-rating tag to docker hub | Admins | BusinessApprovers Developers | Auditors | Admins
|  |  |  | curl -XGET "http://localhost:8765/slack/webhook? pipeline=%GO_PIPELINE_NAME% &instance=%GO_PIPELINE_COUNTER% &stage=%GO_STAGE_NAME%" |  | push the security-rating tag to docker hub | Admins | BusinessApprovers Developers | Auditors | Admins
* increase polling interval using:
wrapper.java.additional.16=-Dcruise.material.update.interval=intervalInMS
in <gocd home>/config/wrapper-server.conf

## Roles
Roles | Chris | Shanti | Josh | Brad | Justin
Administrators | X
Auditors |  |  |  |  | X
Business Approvers |  | X | X
Developers |  |  |  | X

## POC Proof Points
POC Proof Points
Seq | Type | Description
1. | Audit Trail | Trace the origin of an item deployed to production
2. | Audit Trail | Who approved a stage
3. | Audit Trail | What, if any, changes were made to a pipeline
4. | Notifications | Business- and developer-friendly notifications
5. | Approvals | Business friendly interface for notification and approval
6. | Approvals | One approval for many deployable components
7 | Security | Role based access to view, trigger, and change pipelines
7.1. | Security | Admins - all access
7.2. | Security | Developers - Cant create/updates pipelines
7.3. | Security | Business - Can only see "production" pipeline, can approve the "Business Approval" stage
7.4. | Security | Auditors - Read only access to all pipelines